## Resource Utilization
Month : August-2026
Work-Type-wise Resource Utilization
Work Type | Tasks | Expected Hrs | Actual Hrs | Share of Actual Effort | Variance
Support | 266 | 357.5 | 373.75 | 44.3% | 16.25
New Development | 118 | 241 | 269.5 | 31.94% | 28.5
Issue | 23 | 49 | 58 | 6.87% | 9
Enhancement | 15 | 37 | 35.5 | 4.21% | -1.5
Other / Meeting / Change | 61 | 94.5 | 107 | 12.68% | 12.5
Total | 483 | 779 | 843.75 | 100% | 64.75
University-wise Workload Distribution
University / Service | Tasks | Expected Hrs | Actual Hrs | Share of Total Effort
JIWAJI | 87 | 184 | 204 | 24.18%
BHOJ | 96 | 156.5 | 167 | 19.79%
RALVV | 56 | 89.5 | 118 | 13.99%
MGCGV | 69 | 79.25 | 91 | 10.79%
ABVHV | 42 | 65 | 62.5 | 7.41%
APS | 46 | 65 | 61.5 | 7.29%
KTTV | 34 | 60.5 | 61 | 7.23%
COMMAN | 27 | 35.25 | 35.75 | 4.24%
MCBU | 17 | 25.5 | 23 | 2.73%
Carnival Program | 4 | 14 | 14 | 1.66%
Others | 5 | 5.5 | 6 | 0.71%
Resource-wise Utilization
Resource | Tasks | Universities Handled | Actual Hrs | Capacity Utilization
Vandna Khare | 87 | 8 | 187 | 111.3%
Abhishek Rathore | 92 | 10 | 171 | 101.8%
Sakshi Patel | 98 | 5 | 148.25 | 88.24%
Priyanshu Shrivastava | 49 | 1 | 99.5 | 59.23%
Amit Sondhiya | 75 | 6 | 96.5 | 57.44%
Sunil Shende | 82 | 2 | 141 | 83.87%
Total | 483 | — | 843.75 | 71.75%
Weekly Resource Utilization – Overall
Week | Tasks | Active Resources | Expected Hrs | Actual Hrs | Actual vs Expected | Capacity Utilization*
Week 1 (1–7 Aug) | 172 | 5 | 224 | 244.25 | 109% | 87.23%
Week 2 (8–14 Aug) | 132 | 7 | 237 | 262 | 110.5% | 93.57%
Week 3 (15–21 Aug) | 111 | 6 | 205 | 211 | 102.9% | 75.36%
Week 4 (22–28 Aug) | 47 | 4 | 73.5 | 85 | 115.6% | 30.36%
Week 5 (29–31 Aug) | 21 | 6 | 39.5 | 41.5 | 105.1% | 74.11%
Total | 483 | 7 | 779 | 843.75 | 108.3% | 71.75%
Service-wise Attention / Effort %
Service | Effort(Hours) | Effort (%) | Level
JIWAJI | 204 | 24.2% | Very High
BHOJ | 167 | 19.8% | Very High
RALVV | 118 | 14% | High
MGCGV | 91 | 10.8% | High
ABVHV | 62.5 | 7.4% | Medium
APS | 61.5 | 7.3% | Medium
KTTV | 61 | 7.2% | Medium
COMMAN | 35.75 | 4.2% | Low
MCBU | 23 | 2.7% | Low
Others | 20.5 | 2.4% | Low

## Service-wise Utilization
Hours Report
University | Week 1 (1–7 Aug) |  |  |  |  | Week 2 (8–14 Aug) |  |  |  |  | Week 3 (15–21 Aug) |  |  |  |  | Week 4 (22–28 Aug) |  |  |  |  | Week 5 (29–31 Aug) |  |  |  |  | Monthly
| Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other
JIWAJI | 10 | 0 | 0 | 0 | 0 | 18 | 50 | 11.5 | 4 | 0 | 15.5 | 46.5 | 5 | 0 | 0 | 5 | 12.5 | 12.5 | 0 | 1.5 | 7.5 | 0 | 3 | 0 | 1.5 | 56 | 109 | 32 | 4 | 3
BHOJ | 49 | 4 | 10 | 0 | 2.5 | 39 | 2 | 0 | 0 | 6 | 15.5 | 3 | 0 | 9 | 5 | 8.5 | 0 | 3 | 0 | 0 | 4.5 | 0 | 3 | 0 | 3 | 116.5 | 9 | 13 | 9 | 16.5
RALVV | 10 | 25.5 | 5 | 1 | 0 | 2 | 7 | 0 | 10.5 | 0 | 14.5 | 17 | 0 | 0 | 1.5 | 12 | 3.5 | 5 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 42 | 53 | 10 | 11.5 | 1.5
MGCGV | 6.75 | 11 | 0 | 0 | 16.5 | 3 | 31 | 0 | 5 | 0 | 8.75 | 2 | 0 | 0 | 0 | 3.5 | 2.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 46.5 | 0 | 5 | 16.5
ABVHV | 19 | 5.5 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 3.5 | 4 | 0 | 14 | 0 | 3 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 31 | 15.5 | 0 | 16 | 0
APS | 19.5 | 3.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 4 | 0 | 13 | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 47 | 8.5 | 0 | 4 | 2
KTTV | 14.5 | 9.5 | 0 | 0 | 0 | 10 | 3.5 | 0 | 3 | 0 | 7 | 0 | 0 | 7 | 0 | 3.5 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 15 | 0 | 10 | 0
MCBU | 3 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 2.5 | 5.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 4 | 0 | 0 | 0 | 13 | 9.5 | 0 | 0.5 | 0
Others | 0 | 0 | 0 | 0 | 2.5 | 4 | 3.5 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3.5 | 0 | 0 | 12.5
COMMAN | 5 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 12 | 0.25 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 5.25 | 0 | 0 | 0 | 30.5
Percentage Report
University | Week 1 (1–7 Aug) |  |  |  |  | Week 2 (8–14 Aug) |  |  |  |  | Week 3 (15–21 Aug) |  |  |  |  | Week 4 (22–28 Aug) |  |  |  |  | Week 5 (29–31 Aug) |  |  |  |  | Monthly
| Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other
JIWAJI | 100% | 0% | 0% | 0% | 0% | 21.6% | 59.9% | 13.8% | 4.8% | 0% | 23.1% | 69.4% | 7.5% | 0% | 0% | 15.9% | 39.7% | 39.7% | 0% | 4.8% | 62.5% | 0% | 25% | 0% | 12.5% | 27.5% | 53.4% | 15.7% | 2% | 1.5%
BHOJ | 74.8% | 6.1% | 15.3% | 0% | 3.8% | 83% | 4.3% | 0% | 0% | 12.8% | 47.7% | 9.2% | 0% | 27.7% | 15.4% | 73.9% | 0% | 26.1% | 0% | 0% | 42.9% | 0% | 28.6% | 0% | 28.6% | 69.8% | 5.4% | 7.8% | 5.4% | 9.9%
RALVV | 24.1% | 61.4% | 12% | 2.4% | 0% | 10.3% | 35.9% | 0% | 53.8% | 0% | 43.9% | 51.5% | 0% | 0% | 4.5% | 58.5% | 17.1% | 24.4% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 35.6% | 44.9% | 8.5% | 9.7% | 1.3%
MGCGV | 19.7% | 32.1% | 0% | 0% | 48.2% | 7.7% | 79.5% | 0% | 12.8% | 0% | 81.4% | 18.6% | 0% | 0% | 0% | 58.3% | 41.7% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 25.3% | 51.1% | 0% | 5.5% | 18.1%
ABVHV | 77.6% | 22.4% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 16.3% | 18.6% | 0% | 65.1% | 0% | 33.3% | 66.7% | 0% | 0% | 0% | 33.3% | 0% | 0% | 66.7% | 0% | 49.6% | 24.8% | 0% | 25.6% | 0%
APS | 84.8% | 15.2% | 0% | 0% | 0% | 75.8% | 0% | 0% | 24.2% | 0% | 65% | 25% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 76.4% | 13.8% | 0% | 6.5% | 3.3%
KTTV | 60.4% | 39.6% | 0% | 0% | 0% | 60.6% | 21.2% | 0% | 18.2% | 0% | 50% | 0% | 0% | 50% | 0% | 63.6% | 36.4% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 59% | 24.6% | 0% | 16.4% | 0%
MCBU | 100% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 29.4% | 64.7% | 0% | 5.9% | 0% | 0% | 0% | 0% | 0% | 0% | 27.3% | 72.7% | 0% | 0% | 0% | 56.5% | 41.3% | 0% | 2.2% | 0%
OTHERS | 0% | 0% | 0% | 0% | 100% | 22.9% | 20% | 0% | 0% | 57.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 17.5% | 0% | 0% | 62.5%
COMMAN | 31.2% | 0% | 0% | 0% | 68.8% | 0% | 0% | 0% | 0% | 100% | 6.7% | 0% | 0% | 0% | 93.3% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100% | 14.7% | 0% | 0% | 0% | 85.3%

## Horizontal-View
University |  | JIWAJI | BHOJ | RALVV | MGCGV | ABVHV | APS | KTTV | MCBU | OTHERS | COMMAN
Week 1 (1–7 Aug) | Support | 100% | 74.8% | 24.1% | 19.7% | 77.6% | 84.8% | 60.4% | 100% | 0% | 31.2%
| New Development | 0% | 6.1% | 61.4% | 32.1% | 22.4% | 15.2% | 39.6% | 0% | 0% | 0%
| Issue | 0% | 15.3% | 12% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 0% | 2.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Other | 0% | 3.8% | 0% | 48.2% | 0% | 0% | 0% | 0% | 100% | 68.8%
Week 2 (8–14 Aug) | Support | 21.6% | 83% | 10.3% | 7.7% | 100% | 75.8% | 60.6% | 100% | 22.9% | 0%
| New Development | 59.9% | 4.3% | 35.9% | 79.5% | 0% | 0% | 21.2% | 0% | 20% | 0%
| Issue | 13.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 4.8% | 0% | 53.8% | 12.8% | 0% | 24.2% | 18.2% | 0% | 0% | 0%
| Other | 0% | 12.8% | 0% | 0% | 0% | 0% | 0% | 0% | 57.1% | 100%
Week 3 (15–21 Aug) | Support | 23.1% | 47.7% | 43.9% | 81.4% | 16.3% | 65% | 50% | 29.4% | 0% | 6.7%
| New Development | 69.4% | 9.2% | 51.5% | 18.6% | 18.6% | 25% | 0% | 64.7% | 0% | 0%
| Issue | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 27.7% | 0% | 0% | 65.1% | 0% | 50% | 5.9% | 0% | 0%
| Other | 0% | 15.4% | 4.5% | 0% | 0% | 10% | 0% | 0% | 0% | 93.3%
Week 4 (22–28 Aug) | Support | 15.9% | 73.9% | 58.5% | 58.3% | 33.3% | 0% | 63.6% | 0% | 0% | 0%
| New Development | 39.7% | 0% | 17.1% | 41.7% | 66.7% | 0% | 36.4% | 0% | 0% | 0%
| Issue | 39.7% | 26.1% | 24.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Other | 4.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Week 5 (29–31 Aug) | Support | 62.5% | 42.9% | 100% | 100% | 33.3% | 100% | 100% | 27.3% | 0% | 0%
| New Development | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72.7% | 0% | 0%
| Issue | 25% | 28.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 0% | 0% | 0% | 66.7% | 0% | 0% | 0% | 0% | 0%
| Other | 12.5% | 28.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Monthly | Support | 27.5% | 69.8% | 35.6% | 25.3% | 49.6% | 76.4% | 59% | 56.5% | 20% | 14.7%
| New Development | 53.4% | 5.4% | 44.9% | 51.1% | 24.8% | 13.8% | 24.6% | 41.3% | 17.5% | 0%
| Issue | 15.7% | 7.8% | 8.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 2% | 5.4% | 9.7% | 5.5% | 25.6% | 6.5% | 16.4% | 2.2% | 0% | 0%
| Other | 1.5% | 9.9% | 1.3% | 18.1% | 0% | 3.3% | 0% | 0% | 62.5% | 85.3%

## Summary
Most Overloaded Work – August 2026
|  | Actual Effort | Percentage of Utilization | Governance Highlight
Service | JIWAJI | 204 hrs | 24.2% | Highest overall workload; major New Development and Issue effort
Service | BHOJ | 167 hrs | 19.8% | High Support dependency; major operational workload
Resource | Vandna Khare | 187 hrs | 111.3% | Above nominal capacity
Resource | Abhishek Rathore | 171 hrs | 101.8% | Above nominal capacity
Resource | Sakshi Patel | 148.25 hrs | 88.2% | High workload
Task Type | Support | 373.75 hrs | 44.3% | Largest workload category
Task Type | New Development | 269.50 hrs | 31.9% | Major development effort
5 Points That Need Immediate Action
| Task |  | Action
Reduce Workload on JIWAJI and BHOJ | JIWAJI (24.2%) and BHOJ (19.8%) together consumed approximately 44% of total team effort. |  | Review top recurring tasks and create a dedicated optimization plan for both services.
Address Developer Resource Overload | Vandna Khare and Abhishek Rathore are operating at/above nominal capacity, while other resources have available bandwidth. |  | Immediately rebalance tasks and redistribute university/service workload among available developers.
Reduce High Support Dependency | Support consumed 44.3% of total team effort |  | Identify recurring support activities and convert them into Automation, Self-Service, or permanent Application Enhancements.
Improve New Development Planning and Delivery | New Development consumed 31.9% of total effort, with actual effort exceeding planned estimates. |  | Review requirement clarity, effort estimation, task prioritization, and scope management before assigning development activities
Increase Enhancement and Preventive Work | Enhancement activities need stronger focus to reduce future Support and Issue workload. |  | Create a monthly Support → Enhancement → Automation pipeline and prioritize the top recurring problems for permanent resolution.