## Resource Utilization
Month : August 2026
Work-Type-wise Resource Utilization
Work Type | Tasks | Expected Hrs | Actual Hrs | Share of Actual Effort | Variance
Support | 266 | 357.5 | 373.75 | 44.3% | 16.25
New Development | 118 | 241 | 269.5 | 31.94% | 28.5
Issue | 23 | 49 | 58 | 6.87% | 9
Enhancement | 15 | 37 | 35.5 | 4.21% | -1.5
Other / Meeting / Change | 61 | 94.5 | 107 | 12.68% | 12.5
Total | 483 | 779 | 843.75 | 100% | 64.75
Service-wise Workload Distribution
Service / Service | Tasks | Expected Hrs | Actual Hrs | Share of Total Effort
JIWAJI | 87 | 184 | 204 | 24.18%
BHOJ | 96 | 156.5 | 167 | 19.79%
RALVV | 56 | 89.5 | 118 | 13.99%
MGCGV | 69 | 79.25 | 91 | 10.79%
ABVHV | 42 | 65 | 62.5 | 7.41%
APS | 46 | 65 | 61.5 | 7.29%
KTTV | 34 | 60.5 | 61 | 7.23%
Comman | 27 | 35.25 | 35.75 | 4.24%
MCBU | 17 | 25.5 | 23 | 2.73%
Carnival Program | 4 | 14 | 14 | 1.66%
RBLE | 1 | 1 | 3 | 0.36%
Meeting | 3 | 3 | 2.5 | 0.3%
RBLU | 1 | 0.5 | 0.5 | 0.06%
Resource-wise Utilization
Resource | Tasks | Services Handled | Actual Hrs | Capacity Utilization
Vandna Khare | 87 | 8 | 187 | 111.3%
Abhishek Rathore | 92 | 10 | 171 | 101.8%
Sakshi Patel | 98 | 5 | 148.25 | 88.24%
Sunil Shende | 82 | 2 | 141.5 | 84.23%
Priyanshu Shrivastava | 49 | 1 | 99.5 | 59.23%
Amit Sondhiya | 75 | 6 | 96.5 | 57.44%
Total | 483 | - | 843.75 | 83.71%
Weekly Resource Utilization – Overall
Week | Tasks | Active Resources | Expected Hrs | Actual Hrs | Actual vs Expected | Capacity Utilization*
Week 1 (1–7 Aug) | 172 | 5 | 224 | 244.25 | 1.09 | 101.8%
Week 2 (8–14 Aug) | 132 | 6 | 237 | 262 | 1.105 | 109.2%
Week 3 (15–21 Aug) | 111 | 6 | 205 | 211 | 1.029 | 87.92%
Week 4 (22–28 Aug) | 47 | 4 | 73.5 | 85 | 1.156 | 35.42%
Week 5 (29–31 Aug) | 21 | 6 | 39.5 | 41.5 | 1.051 | 17.29%
Total | 483 | 6 | 779 | 843.75 | 1.083 | 83.71%
Service-wise Attention / Effort %
Service | Effort(Hours) | Effort (%) | Level
JIWAJI | 204 | 24.18% | Very High
BHOJ | 167 | 19.79% | Very High
RALVV | 118 | 13.99% | High
MGCGV | 91 | 10.79% | High
ABVHV | 62.5 | 7.41% | Medium
APS | 61.5 | 7.29% | Medium
KTTV | 61 | 7.23% | Medium
Comman | 35.75 | 4.24% | Low
MCBU | 23 | 2.73% | Low
Carnival Program | 14 | 1.66% | Low
RBLE | 3 | 0.36% | Low
Meeting | 2.5 | 0.3% | Low
RBLU | 0.5 | 0.06% | Low

## Service-wise Utilization
Hours Report
Service | Week 1 (1–7 Aug) |  |  |  |  | Week 2 (8–14 Aug) |  |  |  |  | Week 3 (15–21 Aug) |  |  |  |  | Week 4 (22–28 Aug) |  |  |  |  | Week 5 (29–31 Aug)
| Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other
JIWAJI | 10 | 0 | 0 | 0 | 0 | 18 | 50 | 11.5 | 0 | 0 | 15.5 | 46.5 | 5 | 0 | 0 | 5 | 12.5 | 12.5 | 0 | 0 | 7.5 | 0 | 3 | 0 | 0
BHOJ | 49 | 4 | 10 | 0 | 0 | 39 | 2 | 0 | 0 | 0 | 15.5 | 3 | 0 | 9 | 0 | 8.5 | 0 | 3 | 0 | 0 | 4.5 | 0 | 3 | 0 | 0
RALVV | 10 | 25.5 | 5 | 0 | 0 | 2 | 7 | 0 | 0 | 0 | 14.5 | 17 | 0 | 0 | 0 | 12 | 3.5 | 5 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0
MGCGV | 6.75 | 11 | 0 | 0 | 0 | 3 | 31 | 0 | 0 | 0 | 8.75 | 2 | 0 | 0 | 0 | 3.5 | 2.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
ABVHV | 19 | 5.5 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 3.5 | 4 | 0 | 14 | 0 | 3 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0
APS | 19.5 | 3.5 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0 | 0 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
KTTV | 14.5 | 9.5 | 0 | 0 | 0 | 10 | 3.5 | 0 | 3 | 0 | 7 | 0 | 0 | 7 | 0 | 3.5 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Comman | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MCBU | 3 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 2.5 | 5.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 4 | 0 | 0 | 0
Carnival Program | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RBLE | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RBLU | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Percentage Report
Service | Week 1 (1–7 Aug) |  |  |  |  | Week 2 (8–14 Aug) |  |  |  |  | Week 3 (15–21 Aug) |  |  |  |  | Week 4 (22–28 Aug) |  |  |  |  | Week 5 (29–31 Aug)
| Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other | Support | New Development | Issue | Enhancement | Other
JIWAJI | 100% | 0% | 0% | 0% | 0% | 21.6% | 59.9% | 13.8% | 0% | 0% | 23.1% | 69.4% | 7.5% | 0% | 0% | 15.9% | 39.7% | 39.7% | 0% | 0% | 62.5% | 0% | 25% | 0% | 0%
BHOJ | 74.8% | 6.1% | 15.3% | 0% | 0% | 83% | 4.3% | 0% | 0% | 0% | 47.7% | 9.2% | 0% | 27.7% | 0% | 73.9% | 0% | 26.1% | 0% | 0% | 42.9% | 0% | 28.6% | 0% | 0%
RALVV | 24.1% | 61.4% | 12% | 0% | 0% | 10.3% | 35.9% | 0% | 0% | 0% | 43.9% | 51.5% | 0% | 0% | 0% | 58.5% | 17.1% | 24.4% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
MGCGV | 19.7% | 32.1% | 0% | 0% | 0% | 7.7% | 79.5% | 0% | 0% | 0% | 81.4% | 18.6% | 0% | 0% | 0% | 58.3% | 41.7% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
ABVHV | 77.6% | 22.4% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 16.3% | 18.6% | 0% | 65.1% | 0% | 33.3% | 66.7% | 0% | 0% | 0% | 33.3% | 0% | 0% | 66.7% | 0%
APS | 84.8% | 15.2% | 0% | 0% | 0% | 75.8% | 0% | 0% | 0% | 0% | 65% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
KTTV | 60.4% | 39.6% | 0% | 0% | 0% | 60.6% | 21.2% | 0% | 18.2% | 0% | 50% | 0% | 0% | 50% | 0% | 63.6% | 36.4% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
Comman | 31.2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
MCBU | 100% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 29.4% | 64.7% | 0% | 5.9% | 0% | 0% | 0% | 0% | 0% | 0% | 27.3% | 72.7% | 0% | 0% | 0%
Carnival Program | 0% | 0% | 0% | 0% | 0% | 28.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
RBLE | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Meeting | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
RBLU | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Horizontal-View
Service | Work Type | JIWAJI | BHOJ | RALVV | MGCGV | ABVHV | APS | KTTV | Comman | MCBU | Carnival Program
Week 1 (1–7 Aug) | Support | 100% | 74.8% | 24.1% | 19.7% | 77.6% | 84.8% | 60.4% | 31.2% | 100% | 0%
| New Development | 0% | 6.1% | 61.4% | 32.1% | 22.4% | 15.2% | 39.6% | 0% | 0% | 0%
| Issue | 0% | 15.3% | 12% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 2 (8–14 Aug) | Support | 21.6% | 83% | 10.3% | 7.7% | 100% | 75.8% | 60.6% | 0% | 100% | 28.6%
| New Development | 59.9% | 4.3% | 35.9% | 79.5% | 0% | 0% | 21.2% | 0% | 0% | 0%
| Issue | 13.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 0% | 0% | 0% | 0% | 0% | 18.2% | 0% | 0% | 0%
| Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 3 (15–21 Aug) | Support | 23.1% | 47.7% | 43.9% | 81.4% | 16.3% | 65% | 50% | 6.7% | 29.4% | 0%
| New Development | 69.4% | 9.2% | 51.5% | 18.6% | 18.6% | 25% | 0% | 0% | 64.7% | 0%
| Issue | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 27.7% | 0% | 0% | 65.1% | 0% | 50% | 0% | 5.9% | 0%
| Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 4 (22–28 Aug) | Support | 15.9% | 73.9% | 58.5% | 58.3% | 33.3% | 0% | 63.6% | 0% | 0% | 0%
| New Development | 39.7% | 0% | 17.1% | 41.7% | 66.7% | 0% | 36.4% | 0% | 0% | 0%
| Issue | 39.7% | 26.1% | 24.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 5 (29–31 Aug) | Support | 62.5% | 42.9% | 100% | 100% | 33.3% | 100% | 100% | 0% | 27.3% | 0%
| New Development | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72.7% | 0%
| Issue | 25% | 28.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 0% | 0% | 0% | 66.7% | 0% | 0% | 0% | 0% | 0%
| Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Monthly | Support | 27.5% | 69.8% | 35.6% | 25.3% | 49.6% | 76.4% | 59% | 14.7% | 56.5% | 28.6%
| New Development | 53.4% | 5.4% | 44.9% | 51.1% | 24.8% | 13.8% | 24.6% | 0% | 41.3% | 0%
| Issue | 15.7% | 9.6% | 8.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enhancement | 0% | 5.4% | 0% | 0% | 25.6% | 0% | 16.4% | 0% | 2.2% | 0%
| Other | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Summary
Most Overloaded Work – August 2026
Category | Entity Name | Actual Effort | Percentage of Utilization | Governance Highlight
Service | JIWAJI | 204.0 hrs | 24.18% | Highest overall workload (24.18% of team effort); major demand footprint
Service | BHOJ | 167.0 hrs | 19.79% | Substantial ongoing effort (19.79% share); major operational commitment
Service | RALVV | 118.0 hrs | 13.99% | Notable footprint (118.0 hrs logged)
Resource | Vandna Khare | 187.0 hrs | 143.3% | Operating above nominal capacity (+56.5 hrs variance); risk of burnout
Resource | Sakshi Patel | 148.25 hrs | 110.2% | Operating above nominal capacity (+13.75 hrs variance); risk of burnout
5 Points That Need Immediate Action
Point / Focus Area | Observation & Context |  | Recommended Management Action
Reduce Workload on Top Accounts (JIWAJI & BHOJ) | JIWAJI (24.2%) and BHOJ (19.8%) together consumed ~44% of total team capacity. |  | Review top recurring tickets and create a dedicated optimization plan to transition repetitive effort into durable software fixes.
Address Engineer Workload Disparities | Vandna Khare and Abhishek Rathore operated at/above capacity while other team members had available bandwidth. |  | Immediately rebalance assignments and redistribute university/service tasks to available capacity.
Mitigate High Support Dependency | Support activities consumed 44.3% of total team effort across 261 tasks. |  | Identify top recurring queries and convert them into user self-service documentation or platform enhancements.
Improve New Development Estimation & Delivery | New Development experienced the highest absolute variance (+28.5 hrs) over planned estimates. |  | Incorporate historical scope creep buffers into initial project sizing and establish clearer requirements sign-off.
Establish Executive Capacity Guardrails | Individual utilization reached up to 143% during peak delivery windows. |  | Implement bi-weekly governance check-ins to catch overruns early before end-of-month reporting.