## Resource Utilization
Month : August 2026
Work-Type-wise Resource Utilization
Work Type | Tasks | Expected Hrs | Actual Hrs | Share of Actual Effort | Variance
Support | 261 | 357.5 | 373.75 | 44.3% | 16.25
New Development | 118 | 241 | 269.5 | 31.94% | 28.5
Meeting | 42 | 59.5 | 61.5 | 7.29% | 2
Issue | 23 | 49 | 58 | 6.87% | 9
Enhancement | 15 | 37 | 35.5 | 4.21% | -1.5
Change | 9 | 14.5 | 24.5 | 2.9% | 10
Other | 10 | 20.5 | 21 | 2.49% | 0.5
Total | 483 | 779 | 843.75 | 100% | 64.75
Resource-wise Resource Utilization
Resource Name | Tasks | Expected Hrs | Actual Hrs | Variance | Utilization % | Completed | In Progress | Pending
Vandna Khare | 87 | 130.5 | 187 | 56.5 | 143.3% | 65 | 22 | 0
Abhishek Rathore | 91 | 167 | 171 | 4 | 102.4% | 69 | 13 | 10
Sakshi Patel | 98 | 134.5 | 148.25 | 13.75 | 110.2% | 84 | 14 | 0
Sunil Shende | 78 | 139.5 | 141.5 | 2 | 101.4% | 79 | 3 | 0
Priyanshu Shrivastava | 49 | 99.5 | 99.5 | 0 | 100% | 39 | 10 | 0
Amit Sondhiya | 75 | 108 | 96.5 | -11.5 | 89.4% | 66 | 9 | 0
Total | 483 | 779 | 843.75 | 64.75 | 108.3% | 402 | 71 | 10

## Service-wise Utilization
Hours Report – August 2026
Service | Week 1 (1–7 Aug) | [5 empty] | Week 2 (8–14 Aug) | [5 empty] | Week 3 (15–21 Aug) | [5 empty] | Week 4 (22–28 Aug) | [5 empty] | Week 5 (29–31 Aug) | [5 empty] | Period Total
| Support | New Development | Meeting | Issue | Enhancement | Total | Support | New Development | Meeting | Issue | Enhancement | Total | Support | New Development | Meeting | Issue | Enhancement | Total | Support | New Development | Meeting | Issue | Enhancement | Total | Support | New Development | Meeting | Issue | Enhancement | Total
JIWAJI | 10 | 0 | 0 | 0 | 0 | 10 | 18 | 50 | 0 | 11.5 | 0 | 83.5 | 15.5 | 46.5 | 0 | 5 | 0 | 67 | 5 | 12.5 | 1.5 | 12.5 | 0 | 31.5 | 7.5 | 0 | 1.5 | 3 | 0 | 12 | 204
BHOJ | 49 | 4 | 2.5 | 10 | 0 | 65.5 | 39 | 2 | 4 | 0 | 0 | 47 | 15.5 | 3 | 5 | 0 | 9 | 32.5 | 8.5 | 0 | 0 | 3 | 0 | 11.5 | 4.5 | 0 | 2 | 3 | 0 | 10.5 | 167
RALVV | 10 | 25.5 | 0 | 5 | 0 | 41.5 | 2 | 7 | 0 | 0 | 0 | 19.5 | 14.5 | 17 | 0 | 0 | 0 | 33 | 12 | 3.5 | 0 | 5 | 0 | 20.5 | 3.5 | 0 | 0 | 0 | 0 | 3.5 | 118
MGCGV | 6.75 | 11 | 16.5 | 0 | 0 | 34.25 | 3 | 31 | 0 | 0 | 0 | 39 | 8.75 | 2 | 0 | 0 | 0 | 10.75 | 3.5 | 2.5 | 0 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 1 | 91
ABVHV | 19 | 5.5 | 0 | 0 | 0 | 24.5 | 4.5 | 0 | 0 | 0 | 0 | 4.5 | 3.5 | 4 | 0 | 0 | 14 | 21.5 | 3 | 6 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 2 | 3 | 62.5
APS | 19.5 | 3.5 | 0 | 0 | 0 | 23 | 12.5 | 0 | 0 | 0 | 0 | 16.5 | 13 | 5 | 2 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 61.5
KTTV | 14.5 | 9.5 | 0 | 0 | 0 | 24 | 10 | 3.5 | 0 | 0 | 3 | 16.5 | 7 | 0 | 0 | 0 | 7 | 14 | 3.5 | 2 | 0 | 0 | 0 | 5.5 | 1 | 0 | 0 | 0 | 0 | 1 | 61
Comman | 5 | 0 | 11 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 12 | 0.25 | 0 | 0 | 0 | 0 | 3.75 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 35.75
MCBU | 3 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 6 | 2.5 | 5.5 | 0 | 0 | 0.5 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 4 | 0 | 0 | 0 | 5.5 | 23
Carnival Program | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 10 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
RBLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Meeting | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
RBLU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5

## Horizontal-View
Week | Work Type | JIWAJI | BHOJ | RALVV | MGCGV | ABVHV | APS | KTTV | Comman
Week 1 (1–7 Aug) | Support | 100% | 74.8% | 24.1% | 19.7% | 77.6% | 84.8% | 60.4% | 31.2%
Week 1 (1–7 Aug) | New Development | 0% | 6.1% | 61.4% | 32.1% | 22.4% | 15.2% | 39.6% | 0%
Week 1 (1–7 Aug) | Meeting | 0% | 3.8% | 0% | 48.2% | 0% | 0% | 0% | 68.8%
Week 1 (1–7 Aug) | Issue | 0% | 15.3% | 12% | 0% | 0% | 0% | 0% | 0%
Week 1 (1–7 Aug) | Enhancement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 2 (8–14 Aug) | Support | 21.6% | 83% | 10.3% | 7.7% | 100% | 75.8% | 60.6% | 0%
Week 2 (8–14 Aug) | New Development | 59.9% | 4.3% | 35.9% | 79.5% | 0% | 0% | 21.2% | 0%
Week 2 (8–14 Aug) | Meeting | 0% | 8.5% | 0% | 0% | 0% | 0% | 0% | 0%
Week 2 (8–14 Aug) | Issue | 13.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 2 (8–14 Aug) | Enhancement | 0% | 0% | 0% | 0% | 0% | 0% | 18.2% | 0%
Week 3 (15–21 Aug) | Support | 23.1% | 47.7% | 43.9% | 81.4% | 16.3% | 65% | 50% | 6.7%
Week 3 (15–21 Aug) | New Development | 69.4% | 9.2% | 51.5% | 18.6% | 18.6% | 25% | 0% | 0%
Week 3 (15–21 Aug) | Meeting | 0% | 15.4% | 0% | 0% | 0% | 10% | 0% | 0%
Week 3 (15–21 Aug) | Issue | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 3 (15–21 Aug) | Enhancement | 0% | 27.7% | 0% | 0% | 65.1% | 0% | 50% | 0%
Week 4 (22–28 Aug) | Support | 15.9% | 73.9% | 58.5% | 58.3% | 33.3% | 0% | 63.6% | 0%
Week 4 (22–28 Aug) | New Development | 39.7% | 0% | 17.1% | 41.7% | 66.7% | 0% | 36.4% | 0%
Week 4 (22–28 Aug) | Meeting | 4.8% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Week 4 (22–28 Aug) | Issue | 39.7% | 26.1% | 24.4% | 0% | 0% | 0% | 0% | 0%
Week 4 (22–28 Aug) | Enhancement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 5 (29–31 Aug) | Support | 62.5% | 42.9% | 100% | 100% | 33.3% | 100% | 100% | 0%
Week 5 (29–31 Aug) | New Development | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Week 5 (29–31 Aug) | Meeting | 12.5% | 19% | 0% | 0% | 0% | 0% | 0% | 66.7%
Week 5 (29–31 Aug) | Issue | 25% | 28.6% | 0% | 0% | 0% | 0% | 0% | 0%
Week 5 (29–31 Aug) | Enhancement | 0% | 0% | 0% | 0% | 66.7% | 0% | 0% | 0%

## Summary
Most Overloaded Work – August 2026
Category | Entity Name | Actual Effort | Utilization / Share | Governance Highlight
Service | JIWAJI | 204.0 hrs | 24.18% | Highest overall workload (24.18% of team effort); major demand footprint
Service | BHOJ | 167.0 hrs | 19.79% | Substantial ongoing effort (19.79% share); major operational commitment
Service | RALVV | 118.0 hrs | 13.99% | Notable footprint (118.0 hrs logged)
Resource | Vandna Khare | 187.0 hrs | 143.3% | Operating above nominal capacity (+56.5 hrs variance); risk of burnout
Resource | Sakshi Patel | 148.25 hrs | 110.2% | Operating above nominal capacity (+13.75 hrs variance); risk of burnout